## WBS by T- schedule
Event Marketing 101: Partner Guidance: SAMPLE EVENT WORK BACK SCHEDULE To use this suggested schedule, change the Event Date with the date you want to hold the event and the other due dates will auto populate based on the Days Before/After that this task needs to be completed. Hover over any of the cells with the red triangle to see additional comments. For your complete Event Marketing 101 Toolkit, please refer to additional ‘Partner Guidance’ documents and ‘Partner Templates’
Event Work Back Schedule
Week | Complete | Category | Task | Days Before/After | 2016-07-15
T-13 |  | Planning: | Event goal and objectives | -42 | 2016-06-03
T-13 |  | Planning: | Budget | -42 | 2016-06-03
T-13 |  | Planning: | Type of event and target audience | -42 | 2016-06-03
T-12 |  | Planning: | Confirm venue with set date and time | -42 | 2016-06-03
T-12 |  | Planning: | Confirm presenters | -35 | 2016-06-10
T-12 |  | Planning: | Sponsorship and fees | -35 | 2016-06-10
T-12 |  | Planning: | Attendee fees | -35 | 2016-08-19
T-6 |  | Marketing: | Creative concept decided | -35 | 2016-06-10
T-6 |  | Marketing: | Create marketing pieces | -28 | 2016-06-03
T-6 |  | Presentation Content: | Presentation planning | -28 | 2016-06-17
T-6 |  | Marketing: | Develop promotional offer | -28 | 2016-06-03
T-6 |  | Marketing: | Pre-event email marketing - wave 1 | -28 | 2016-06-03
T-5 |  | Marketing: | Schedule a series of Social Media updates | -21 | 2016-06-03
T-5 |  | Marketing: | Set-up event hashtag for Twitter | -21 | 2016-06-03
T-5 |  | Marketing: | Direct mail send out | -21 | 2016-06-24
T-5 |  | Presentation Content: | Create presentation outline | -21 | 2016-06-24
T-4 |  | Marketing: | Draft and post Social Media blog | -25 | 2016-06-03
T-4 |  | Marketing: | Reference event on Linkedin and Facebook pages | -25 | 2016-06-03
T-3 |  | Logistics: | Plan for follow-up action | -21 | 2016-06-24
T-3 |  | Marketing: | Pre-event telemarketing | -21 | 2016-06-24
T-3 |  | Marketing: | Pre-event email marketing - wave 2 | -21 | 2016-06-24
T-3 |  | Presentation Content: | Create presentation draft | -21 | 2016-06-24
T-2 |  | Logistics: | Venue check | -14 | 2016-07-01
T-2 |  | Logistics: | Collateral, Handouts and Giveaways to be decided & ordered | -14 | 2016-07-01
T-1 |  | Logistics: | Catering confirmed | -14 | 2016-07-01
T-1 |  | Presentation Content: | Conduct run through | -7 | 2016-07-08
T-1 |  | Presentation Content: | Back-up plan for Presenters, Hardware, Software and AV | -7 | 2016-07-08
T-1 |  | Marketing: | Confirm attendance | -3 | 2016-07-12
T-1 |  | Presentation Content: | Finalize presentation | -3 | 2016-07-12
T-0 |  | Event Day: | Event Day | 0 | 2016-07-15
T+1 |  | Post Event: | Follow up action decided as per plan | 1 | 2016-07-14
T+1 |  | Post Event: | Follow action put into place | 2 | 2016-07-13
T+1 |  | Post Event: | Collaboration and analysis of feedback | 2 | 2016-07-13
T+1 |  | Post Event: | Reconcilliation of budget | 4 | 2016-07-19
Note on D7: Brian LaMee: What is your overall goal for the completion of this event? What is the purpose and call to action to achieve the overall goal? For example it might not be enough to justify expenditure of going forward with the event by simply outlining a goal of "increase sales" a specific tactic plan will have to be considered and targets set.
Note on D15: Jessica Dziubinski: Create pieces for driving target audience to the event. Templates have been provided for Partner ease of use.
Note on D16: Brian LaMee: Begin with the idea generation phase and brainstorm all the topics that can be presented
Note on D25: Brian LaMee: You want to plan follow up action items for those that did attend and those that could not make it. "Call me" is not an action item. Plan webcasts, additional events, whitepapers, evaluations, etc. This gives people multiple action items they could do.
Note on D29: Brian LaMee: If you are not familiar with the location or you have never held an event there before, make sure you do a walk through before the day of the actual event.
Note on F36: Brian LaMee: Plug in the date when you would like to hold your event, the rest of the dates will calculate.
Note on D37: Jessica Dziubinski: Gather evaluation and feedback then communicate a follow up action and begin this process.
Note on D38: Brian LaMee: Send a "Thank You" to those that attended and remind them of the action items you talked about in the event. Send a "Sorry we missed you" to those that did not attend and give them options on how they could get the materials or see a webcast to get the information.

## WBS by Activity
Test Prep Professionals: SAMPLE EVENT WORK BACK SCHEDULE To use this suggested schedule, change the Event Date with the date you want to hold the event and the other due dates will auto populate based on the Days Before/After that this task needs to be completed. Hover over any of the cells with the red triangle to see additional comments.
Event Work Back Schedule
Complete | Task | Days Before/After | Due Date
Planning:
| Goal and objectives | 42 | 2016-06-20
| Budget | 42 | 2016-06-20
| Type of event and target audience | 42 | 2016-06-20
| Confirm venue with set date and time | 28 | 2016-07-04
| Confirm presenter(s) | 28 | 2016-07-04
| Sponsorship and fees | 35 | 2016-06-27
| Attendee fees | 35 | 2016-06-27
Logistics:
| Plan for follow-up action | 21 | 2016-07-11
| Venue check | 14 | 2016-07-18
| Collateral, Handouts and Giveaways to be decided | 14 | 2016-07-18
| Enter your own action item | 14 | 2016-07-18
| Confirm attendance | 3 | 2016-07-01
Marketing:
| Creative concept decided | 42 | 2016-07-04
| Create marketing pieces | 42 | 2016-06-20
| Develop promotional offer | 42 | 2016-07-04
| Pre- event email marketing - wave 1 | 28 | 2016-07-04
| Schedule series of Social Media communications and updates | 28 | 2016-07-04
| Social Media communications and updates | 28 | 2016-07-04
| Social Media communications and updates | 21 | 2016-06-06
| Social Media communications and updates | 14 | 2016-06-13
| Draft and post Social Media blog | 28 | 2016-07-04
| Set-up event hashtag for Twitter | 21 | 2016-07-04
| Reference to LinkedIn and Facebook pages | 21 | 2016-07-04
| Direct mail send out | 21 | 2016-07-11
| Pre-event telemarketing if applicable | 21 | 2016-07-11
| Pre- event email marketing - wave 2 | 10 | 2016-07-22
Presentation Content:
| Presentation planning | 42 | 2016-06-20
| Create presentation outline | 35 | 2016-06-27
| Create presentation draft | 21 | 2016-07-11
| Conduct run through | 7 | 2016-07-25
| Back-up plan for Presenters, Hardware, Software and AV | 21 | 2016-07-11
| Finalize presentation | 3 | 2016-07-04
| Event Day |  | 2016-08-01
Post Event:
| Follow up action decided as per plan | 1 | 2016-08-02
| Follow action put into place | 2 | 2016-08-03
| Collaboration and analysis of feedback | 2 | 2016-08-03
| Reconcilliation of budget | 4 | 2016-08-07
Formulas:
Due Date = D47-[Days Before/After]
Due Date = D47-[Days Before/After, row below]